## project budget
CareLink HMS Implementation Project - Budget
Category | Estimated Quantity | Estimated Cost per Unit | Estimated Subtotal | Notes
Execution | days | $ |  | Configuration, integration & delivery labour (Months 3-9)
Project Manager | 100 | 600 | 60000 | 100 days @ $600/day managing execution phase
Business Analyst (1) | 60 | 550 | 33000 | 60 days @ $550/day requirements/process analysis
Config/Integration Specialists (3) | 300 | 650 | 195000 | 3 specialists, 300 days total @ $650/day (config + integration)
UX/Reports Designer | 20 | 600 | 12000 | 20 days @ $600/day designing screens/reports
Costs Total |  |  | 300000
Initiation
Project Manager | 20 | 600 | 12000 | 20 days @ $600/day charter & planning
UX/Reports Designer | 10 | 600 | 6000 | 10 days @ $600/day early design input
Configuration Team (Reqs & Vendor Eval) | 40 | 600 | 24000 | 40 days @ $600/day requirements & vendor evaluation
Costs Total |  |  | 42000
Other WBS Structure Item (Level 2): Testing
Testing Support by Vendor |  |  | 120000 | Fixed-price vendor SIT/UAT support (assumption, per quote)
Networking Costs Total |  |  | 120000
Training
Trainer | 60 | 900 | 54000 | 60 trainer-days @ $900/day across NSW/VIC sites
Costs Subtotal |  |  | 54000
Software, Cloud Hosting & Overheads (Misc.)
Cloud Hosting Setup (SaaS) | 1 | 60000 | 60000 | SaaS hosting/setup only - no on-prem hardware upgrade
HMS Software Licence (Year 1) | 1 | 850000 | 850000 | Year 1 HMS platform licence fee (assumption, per vendor quote)
Costs Subtotal |  |  | 910000
Services
Data Migration & Integration Tools | 1 | 130000 | 130000 | Data migration/integration tooling (assumption)
Services Subtotal |  |  | 130000
Additional Costs
Overhead | 1 | 68400 | 68400 | 20% of Execution+Initiation labour, per overhead policy
Additional Costs Subtotal |  |  | 68400
Costs Total |  |  | 1624400
Contingency
Reserve | 1 | 162440 | 162440 | 10% contingency reserve on total project cost
162440
GRAND TOTAL |  |  |  | 1786840

## Budget Charts
Budget Summary by Category
Category | Amount (AUD)
Execution (labour) | 300000
Initiation (labour) | 42000
Testing (vendor) | 120000
Training | 54000
Software/Cloud/Overheads | 910000
Services | 130000
Additional Costs (Overhead) | 68400
Contingency Reserve | 162440